KENYA COUNTY TRANSITION BENCHMARKING, OWNERSHIP

AND CAPACITY OUTCOME MONITORING TOOL

for

Monitoring Transition of the PEPFAR-supported HIV/TB programme

from currently Implementing Partners to the County Health Departments

Adapted from ICF International for Kenya County Transition Teams

Modified by the PEPFAR and the Council of Governors Team of Experts

November, 2021

Version 3.2

The tool presented in this document operationalize the process of monitoring the transition of the HIV/TB program in Counties as outlined in the implementation plan designed by PEPFAR/CoG HIV and Tuberculosis Program Kenya Health System and Services Team.  This tool forms the basis of the transition monitoring for all of PEPFAR-supported counties.  County Transition Teams (CTTs) may have additional transition monitoring requirements that go beyond this tool. This tool will also be standardized for HIV/TB transition monitoring at national level.

The indicators outlined in this document include:

- Transition benchmarking indicators: These indicators assess the level of involvement of the CDOH and that of the Implementing Partner in supporting the county in selected HIV/TB key domains. The transition to local ownership is measured from two perspectives: first, withdrawal from management activities by the PEPFAR-funded Implementing Partner; and second, assumption of management activities for the HIV program by the County health department. The transition benchmarking indicators cover the areas of Leadership and Governance, HIV service delivery, finance, supply chain support, laboratory, human resources and health information.

- Institutional ownership indicators: These indicators measure the institutional ownership at the county level with regard to provision of HIV services by the health system. The ownership indicators cover three domains: Operationalization of national HIV plan at institutional level, institutional coordination of HIV service provision activities, and congruence of expectations between levels of the health system.

- Capacity outcome indicators: Ensuring adequate capacity to manage and deliver quality services is also a key component of readiness for transition to county ownership.  Indicators for monitoring key county capacity outcomes have been identified based on HIV programming in Kenya.

- Program Results: The goal of all HIV programs is improved coverage and quality of services and improved health for beneficiaries. Progress towards transition will be evaluated in light of these results, using accepted County and PEPFAR indicators (ideally aligned with the Government of Kenya’s/NASCOP monitoring tool standards).

Data collection and reporting process:

Data on the above-mentioned indicators for each county will be collected as a two-step process.

- Data collection will be done by the County Transition Team who will report on the above-mentioned indicators for their county in order to assess the progress in transition, institutional ownership and capacity development in relation to program results. County Transition Teams will compile the information.

- These data will be included in the 1st quarter county profile compiled by PEPFAR agencie which contains data for the past year, and will be validated by PEPFAR staff during upcoming site visits in order to get a more comprehensive understanding of the transition process. Particular emphasis will be given to the institutional ownership indicators.

Table of Contents

TRANSITION BENCHMARKING INDICATORS	8

COUNTY LEVEL LEADERSHIP AND GOVERNANCE	8

Indicator T1: Transition of County Legislature Health Leadership and Governance	8

Indicator T2: Transition of County Executive (County Health Management Team (CHMT)) in Health Leadership and Governance	10

Indicator T3: Transition of County Health Planning: Level of Autonomy of the CDOH.	12

COUNTY LEVEL ROUTINE SUPERVISION AND MENTORSHIP	14

Indicator T4A: Transition of routine Supervision and Mentorship: Level of Involvement of the Implementing Partner	14

Indicator T4B: Transition of routine Supervision and mentorship: Level of Autonomy of the CDOH	15

COUNTY LEVEL HIV/TB PROGRAM SPECIAL INITIATIVES (eg, RRI, Leap, Surge, SIMS)	17

Indicator T5A: Transition of HIV/TB program special initiatives eg, (RRI, Leap, Surge, SIMS) :  Level of Involvement of the Implementing Partner	17

Indicator T5B: Transition of HIV program special initiatives eg (RRI, Leap, Surge, SIMS): Level of Autonomy of the CDOH	18

COUNTY LEVEL QUALITY IMPROVEMENT	19

Indicator T6A: Transition of Quality Improvement (QI): Level of Involvement of the Implementing Partner	19

Indicator T6B: Transition of Quality Improvement: Level of Autonomy of the CDOH	20

COUNTY LEVEL HIV/TB PATIENT IDENTIFICATION AND LINKAGE TO TREATMENT	21

Indicator T7A: Transition of Patient identification and linkage to treatment : Level of Involvement of the Implementing Partner	21

Indicator T7B: Transition of Patient identification and linkage to treatment : Level of Autonomy of the CDOH	22

CoUNTY LEVEL PATIENT RETENTION, ADHERENCE AND VIRAL SUPPRESSION SERVICES	24

Indicator T8A: Transition of Patient retention, adherence and Viral suppression services: Level of Involvement of the Implementing Partner	24

Indicator T8B: Transition of Patient retention, adherence and Viral suppression services: : Level of Autonomy of the CDOH	25

COUNTY LEVEL HIV PREVENTION AND KEY POPULATION SERVICES	27

Indicator T9A: Transition of HIV/TB prevention and Key population services : Level of Involvement of the Implementing Partner	27

Indicator T9B: Transition of HIV prevention and Key population services : Level of Autonomy of the CDOH	28

COUNTY LEVEL FINANCE MANAGEMENT	29

Indicator T10A: Transition of Financial Management: Level of Involvement of the Implementing Partner	29

Indicator T10B: Transition of Financial Management: Level of Autonomy of the CDOH	30

COUNTY LEVEL MANAGING SUB-GRANTS	31

Indicator T11A: Transition of Managing Sub-Grants: Level of Involvement of the Implementing Partner	31

Indicator T11B: Transition of Managing Sub-Grants: Level of Autonomy of the CDOH	31

COUNTY LEVEL COMMODITIES MANAGEMENT	33

Indicator T12A: Transition of Commodities Management: Level of Involvement of the Implementing Partner	33

Indicator T12B: Transition of Commodities Management: Level of Autonomy of the CDOH	33

COUNTY LEVEL EQUIPMENT PROCUREMENT AND USE	35

Indicator T13A: Transition of Equipment Procurement and Use: Level of Involvement of the Implementing Partner	35

Indicator T13B: Transition of Procurement and Use: Level of Autonomy of the CountyCDOH	35

COUNTY LEVEL LABORATORY SERVICES	37

Indicator T14A: Transition of Laboratory Services: Level of Involvement of the Implementing Partner	37

Indicator T14B: Transition of Laboratory Services: Level of Autonomy of the CDOH	38

COUNTY LEVEL INVENTORY MANAGEMENT	39

Indicator T15A: Transition of Inventory Management for Equipment & Commodities: Level of Involvement of the Implementing Partner	39

Indicator T15B: Transition of Inventory Management for Equipment & Commodities: Level of Autonomy of the CDOH	40

COUNTY LEVEL IN-SERVICE TRAINING	41

Indicator T16A: Transition of In-service Training: Level of Involvement of the Implementing Partner	41

Indicator T16B: Transition of In-service Training: Level of Autonomy of the CDOH	41

COUNTY LEVEL HUMAN RESOURCE MANAGEMENT	43

Indicator T17A: Transition of HIV/TB Human Resource Management: Level of Involvement of the Implementing Partner	43

Indicator T17B: Transition of HIV/TB Human Resource Management: Level of Autonomy of the CDOH	44

COUNTY LEVEL HIV/TB PROGRAM DATA MANAGEMENT	45

Indicator T18A: Transition of HIV/TB Program Data Management: Level of Involvement of the Implementing Partner	45

Indicator T18B: Transition of HIV/TB Program Data Management: Level of Autonomy of the CDOH	45

COUNTY LEVEL PATIENT MONITORING SYSTEM	47

Indicator T19A: Transition of Patient Monitoring System: Level of Involvement of the Implementing Partner	47

Indicator T19B: Transition of Patient Monitoring System: Level of Autonomy of the CDOH	47

COUNTY LEVEL INSTITUTIONAL OWNERSHIP INDICATOR	49

Indicator IO.1:Operationalization of national HIV/TB plan at institutional level	49

Indicator IO.2: Institutional coordination of HIV/TB prevention, care and treatment activities	50

Indicator IO.3: Congruence of expectations between levels of the health system	51

# TRANSITION BENCHMARKING INDICATORS

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL LEADERSHIP AND GOVERNANCE

## Indicator T1: Transition of County Legislature Health Leadership and Governance

| To what degree is the County Legislature involved in Leadership and Governance of HIV/TB services? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fully adequate with evidence |  | Partially adequate with evidence | Structures/ functions defined some evidence | Structures/ functions defined NO evidence | Inadequate structures/ functions | Number |
| T1.1. Does the county have a legally constituted mechanism that oversees the health department? e.g. County assembly health committee | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.2. Does the county have an overall vision for the County Department of Health (CDOH) that is overseen by the County assembly health committee? (Check if the vision statement is included in County integrated development plan (CIDP)) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.3 Are the roles of the County assembly health committee well-defined in the county health system? (Review the county assembly standing orders in respect to the health committee) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.4 Are County assembly health committee meetings held regularly as stipulated; decisions documented; and reflect accountability and resource stewardship? (check County assembly health committee minutes) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.5 Does the County assembly health committee composition include members who are recognized for leadership and/or area of expertise and are representative of stakeholders including PLHIV/TB patients? e.g. PLHIV ex officio members (check County assembly health committee minutes) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.6 Does the County assembly health committee ensure that public interest is considered in decision making? e.g. the transparency of the public participation (check assembly public participation standing rules) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.7 How committed and accountable is the County assembly health committee in following up on agreed action items? (Check minutes) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.8 Does the County assembly health committee have a risk management policy/framework? (check the committee’s standing rules) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.9 How much oversight is given to HIV/TB activities in the county by the health committee of the county assembly? (Check minutes of previous meetings) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.10 Is the leadership arrangement/structure for the HIV/TB program adequate to increase coverage and quality of HIV/TB services? (Review and compare the HIV/TB services organogram with that of the IP to find areas requiring strengthening) | 4 |  | 3 | 2 | 1 | 0 |  |
| T1.11 Does the HIV/TB program planning and funding allow for sustainability? (review annual workplan (AWP) and CIDP) | 4 |  | 3 | 2 | 1 | 0 |  |
| Total CDOH = |  |  |  |  |  |  |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of County Legislature Leadership and Governance: ☐ 0–13: Low ☐ 14–28: Medium ☐ 29–43: High ☐ 44: Full Performance |  |  |  |  |  |  |  |

Comments

## Indicator T2: Transition of County Executive (County Health Management Team (CHMT)) in Health Leadership and Governance

| To what degree is the CHMT involved in Leadership and Governance of HIV/TB services? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Fully adequate with evidence |  | Partially adequate with evidence | Structures/ functions defined some evidence | Structures/ functions defined NO evidence | Inadequate structures/ functions | Number |  |
| T2.1. Is the CHMT responsive to the requirements of the County’s Oversight structures, i.e. County assembly health committee? (See if CHMT has minutes for regular meetings with the County Health Committee) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.2. Is the CHMT accountable to clients/patients seeking services within the county? (CHMT to demonstrate review of feedback from clients/patients) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.3 Is the CHMT involving the private sector and community based organizations in the planning of health services including HIV/TB services? (Check CHMT/Private sector/CBO meeting minutes) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.4 Are CHMT meetings held regularly as stipulated; decisions documented including for the HIV/TB program; and reflect accountability and resource stewardship? (check CHMT minutes) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.5 Is the CHMT implementing policies and regulations set by national level? (Check if CHMT releases circulars informing HCW and the public of national policies e.g. no charges for all HIV/TB services) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.6 Does the CHMT hold joint monitoring teams and joint high-level meetings with development partners supporting the county? (Check CHMT/Development partners minutes) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.7 Does the CHMT plan and manage health services to meet local needs? (Check if the last Annual Performance Review report achieved ≥70% overall targets in the last FY) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.8 Does the CHMT mobilize local resources for the HIV/TB program? (Check the county expenditure reports) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.9 Is the CHMT involved in the supervision of HIV/TB services in the county? (Check supervision reports) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.10 Has the CHMT ensured that the leadership arrangement/structure for the HIV/TB program is adequate to increase coverage and quality of HIV/TB services? (Review to compare the HIV/TB services organogram with that of the IP to find areas requiring strengthening) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| T2.11 Has the CHMT ensured that the HIV/TB program planning and funding allow for sustainability? (Review annual workplan (AWP) and CIDP) | 4 |  | 3 | 2 | 1 | 0 |  |  |
| Total CDOH = |  |  |  |  |  |  |  |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |
| Level of CHMT Leadership and Governance: ☐ 0–13: Low ☐ 14–28: Medium ☐ 29–43: High ☐ 44: Full Performance |  |  |  |  |  |  |  |  |

Comments

COUNTY LEVEL PLANNING

## Indicator T3: Transition of County Health Planning: Level of Autonomy of the CDOH.

| To what degree is the County involved in HIV/TB Services Health Planning? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Not involved |  | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| T3.1 Creating a costed county annual work plan for HIV/TB services (Check the health sector AWP to see if HIV/TB services are included and costed) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.2 Identifying key HIV program priorities that sustains good coverage and high HIV service quality (Check if the county prioritizes HIV/AIDS and if its priorities align with National/PEPFAR priorities) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.3 Track implementation of the costed county annual work plan for HIV/TB services (check the health sector AWP to see if HIV/TB services are included and costed) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.4 Identifying HRH needs for HIV/TB that will support the delivery of the agreed package of activities (Check at the county’s HRH plan if it includes HRH for HIV/TB and transitioning of HIV/TB services and compare with current PEPFAR HRH investments) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.5 Having in place a system for forecasting, including HRH needs for HIV/TB (Check the CIDP if it has incremental allocation of resources in successive years) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.6 Coordinating the scope of activities and resource contributions of all partners for HIV/TB in county (Check for county partner/stakeholders documentations) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.7 Convening meetings with key county HIV/TB services program staff and implementing partners to review performance (check for partner performance review minutes) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.8 Convening meetings with community HIV/TB stakeholders to review community needs (check for community stakeholders meetings minutes) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.9 Convening to review program performance for HIV/TB (check for program performance review meetings minutes) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.10 Providing technical guidance for county AIDS/TB coordination (check if county has an integrated county workplan for all partners/stakeholders within the county) | 0 |  | 1 | 2 | 3 | 4 |  |
| T3.11 Providing support to the County AIDS Committee (county to demonstrate support) | 0 |  | 1 | 2 | 3 | 4 |  |
| Total CDOH = |  |  |  |  |  |  |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of County Health Planning: ☐ 0–13: Low ☐ 14–28: Medium ☐ 29–43: High ☐ 44: Full Performance |  |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL ROUTINE SUPERVISION AND MENTORSHIP

## Indicator T4A: Transition of routine Supervision and Mentorship: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of SUPERVISION AND MENTORSHIP FOR THE HIV/TB PROGRAMME? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T4A.1 Developing the county HIV/TB programme routine supervision plan | 4 | 3 | 2 | 1 | 0 | 4 |  |
| T4A.2 Arranging logistics, including vehicle and/or fuel | 4 | 3 | 2 | 1 | 0 | 2 |  |
| T4A.3 Conducting routine supervision visits to county (public)/private/faith-based facilities | 4 | 3 | 2 | 1 | 0 | 3 |  |
| T4A.4 Completing supervision checklist | 4 | 3 | 2 | 1 | 0 | 3 |  |
| T4A.5 Mobilizing support to address issues identified during supervision | 4 | 3 | 2 | 1 | 0 | 2 |  |
| T4A.6 Financial facilitation for county supervision (paying allowances to supervisors) | 4 | 3 | 2 | 1 | 0 | 4 |  |
| T4A.7 Developing the action plan and following up on issues identified during the supervision | 4 | 3 | 2 | 1 | 0 | 3 |  |
| T4A.8 Planning for staff mentorship including cross learning visits | 4 | 3 | 2 | 1 | 0 | 3 |  |
| T4A.9 Spending time with staff to identify individual’s strengths | 4 | 3 | 2 | 1 | 0 | 2 |  |
| T4A.10 Identifying and working with facility staff to pursue mentorship goals | 4 | 3 | 2 | 1 | 0 | 2 |  |
| T4A.11 Paying for mentorship activities | 4 | 3 | 2 | 1 | 0 | 4 |  |
| T4A.12 Documenting outcomes of the mentorship | 4 | 3 | 2 | 1 | 0 | 4 |  |
| Total Implementing Partner = |  |  |  |  |  | 38 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of Involvement of IP in Supervision: ☒ 48–32: High ☒ 31–16: Medium ☐ 15–1: Low ☒ 0: Phased Out |  |  |  |  |  |  |  |

## Indicator T4B: Transition of routine Supervision and mentorship: Level of Autonomy of the CDOH

| To what degree is the County Department of Health involved in each of the following aspects of SUPERVISION AND MENTORSHIP FOR THE HIV/TB PROGRAMME? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T4B.1 Developing the county HIV/TB supervision plan | 0 | 1 | 2 | 3 | 4 | 3 |
| T4B.2 Arranging logistics, including vehicle and/or fuel | 0 | 1 | 2 | 3 | 4 | 2 |
| T4B.3 Conducting supervision visits to county (public)/private/faith-based facilities | 0 | 1 | 2 | 3 | 4 | 4 |
| T4B.4 Completing supervision forms | 0 | 1 | 2 | 3 | 4 | 4 |
| T4B.5 Mobilizing support to address issues identified during supervision | 0 | 1 | 2 | 3 | 4 | 2 |
| T4B.6 Financial facilitation for county supervision (paying allowances to supervisors) | 0 | 1 | 2 | 3 | 4 | 0 |
| T4B.7 Developing the action plan and following up on issues identified during the supervision | 0 | 1 | 2 | 3 | 4 | 2 |
| T4B.8 Planning for staff mentorship including cross learning visits | 0 | 1 | 2 | 3 | 4 | 2 |
| T4B.9 Spending time with staff to identify individual’s strengths | 0 | 1 | 2 | 3 | 4 | 3 |
| T4B.10 Identify and working with facility staff to persue mentorship goals | 0 | 1 | 2 | 3 | 4 | 2 |
| T4B.11 Paying for mentorship activities | 0 | 1 | 2 | 3 | 4 | 0 |
| T4B.12 Documenting outcomes of the mentorship | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 27 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in Supervision: ☐ 0–15: Low ☒ 16–31: Medium ☐ 32–47: High ☐ 48: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL HIV/TB PROGRAM SPECIAL INITIATIVES (eg, RRI, Leap, Surge, SIMS)

## Indicator T5A: Transition of HIV/TB program special initiatives eg, (RRI, Leap, Surge, SIMS) :  Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB PROGRAM SPECIAL INITIATIVES (eg, RRI, LEAP, SURGE SIMS)? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T5A.1 Developing the county RRI, LEAP, Surge or SIMS plan or any other initiative | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T5A.2 Arranging logistics, including vehicle and/or fuel | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T5A.3 Conducting, LEAP, SURGE, SIMS or RRI visits or any other initiative to public/private/faith based facilities | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T5A.4 Completing relevant initiative tools / reporting templates | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T5A.5 Mobilizing support to address issues identified during site visits | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T5A.6 Financial facilitation for site visits (paying allowances to the team) | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T5A.7 Developing the action plan and following up on issues identified during site visits | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T5A.8 Reporting special initiative implementation progress to higher levels. Ie, Reporting: Documenting, tracking and supporting timely and accurate reporting of top line indicators | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| Total Implementing Partner = |  |  |  |  |  |  | 25 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |
| Level of Involvement of IP in special initiatives: ☒ 32–21: High ☐ 20–10: Medium ☐ 9–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |

## Indicator T5B: Transition of HIV program special initiatives eg (RRI, Leap, Surge, SIMS): Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB PROGRAM SPECIAL INITIATIVES (eg, RRI, LEAP, SURGE, SIMS)? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T5B.1 Developing the county RRI, LEAP, Surge or SIMS plan or any other initiative | 0 | 1 | 2 | 3 | 4 | 1 |
| T5B.2 Arranging logistics, including vehicle and/or fuel | 0 | 1 | 2 | 3 | 4 | 1 |
| T5B.3 Conducting, LEAP, SURGE, SIMS or RRI visits to public/private/faith based facilities | 0 | 1 | 2 | 3 | 4 | 2 |
| T5B.4 Completing relevant initiative tools/ reporting templates | 0 | 1 | 2 | 3 | 4 | 2 |
| T5B.5 Mobilizing support to address issues identified during site visits | 0 | 1 | 2 | 3 | 4 | 3 |
| T5B.6 Financial facilitation for site visits (paying per diems/ lunches the team) | 0 | 1 | 2 | 3 | 4 | 0 |
| T5B.7 Developing the action plan and following up on issues identified during site visits | 0 | 1 | 2 | 3 | 4 | 2 |
| T5B.8 Reporting special initiative implementation progress to higher levels. ie Reporting: Documenting, tracking and supporting timely and accurate reporting of top line indicators | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 14 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in special initiatives : ☐ 0–9: Low ☒ 10–20: Medium ☐ 21–31: High ☐ 32: Full Autonomy |  |  |  |  |  |  |

Comments

# COUNTY LEVEL QUALITY IMPROVEMENT

## Indicator T6A: Transition of Quality Improvement (QI): Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB QUALITY IMPROVEMENT (QI)? |  |  |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation |  | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T6A.1 Selecting priorities and developing / adapting QI plan | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |
| T6A.2 Training facility staff | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |
| T6A.3 Providing technical support to QI teams | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |
| T6A.4 Reviewing/tracking facility QI reports | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |
| T6A.5 Funding QI Initiatives | 4 |  | 3 |  | 2 | 1 | 0 | 4 |  |
| T6A.6 Other support QI activities | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |
| T6A.7 Convening/managing county-wide QI forum | 4 |  | 3 |  | 2 | 1 | 0 | 2 |  |
| Total Implementing Partner = |  |  |  |  |  |  |  | 21 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |  |
| Level of Involvement of IP in Quality Improvement: ☒ 28–19: High ☐ 18–9 Medium ☐ 8–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |  |

## Indicator T6B: Transition of Quality Improvement: Level of Autonomy of the CDOH

| To what degree is CDOH involved in each of the following aspects of HIV/TB QUALITY IMPROVEMENT? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T6B.1 Selecting priorities and developing/adapting QI plan | 0 | 1 | 2 | 3 | 4 | 2 |
| T6B.2 Training facility staff | 0 | 1 | 2 | 3 | 4 | 2 |
| T6B.3 Providing technical support to QI teams | 0 | 1 | 2 | 3 | 4 | 2 |
| T6B.4 Reviewing/tracking facility QI reports | 0 | 1 | 2 | 3 | 4 | 2 |
| T6B.5 Funding QI Initiatives | 0 | 1 | 2 | 3 | 4 | 0 |
| T6B.6 Other support QI activities | 0 | 1 | 2 | 3 | 4 | 1 |
| T6B.7 Convening/managing county-wide QI forum | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 12 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in Quality Improvement: ☐ 0–8: Low ☐ 9–17: Medium ☐ 18–27: High ☐ 28: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL HIV/TB PATIENT IDENTIFICATION AND LINKAGE TO TREATMENT

## Indicator T7A: Transition of Patient identification and linkage to treatment : Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB PATIENT IDENTIFICATION AND LINKAGE TO TREATMENT ? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T7A.1 Recruitment of HIV testing services (HTS) counselors | 4 | 3 | 2 | 1 | 0 | 3 |
| T7A.2 Remuneration of HIV testing counselors (Funds for paying HTS Counselors) | 4 | 3 | 2 | 1 | 0 | 3 |
| T7A.3 Ensuring that HTS eligibility screening registers and SOPS are available | 4 | 3 | 2 | 1 | 0 | 2 |
| T7A.4 Ensuring that HIV testing consumables/supplies eg methylated spirit, gloves lancets etc. are available | 4 | 3 | 2 | 1 | 0 | 2 |
| T7A.5 Ensuring availability of adequate and appropriate HIV testing space/ environment | 4 | 3 | 2 | 1 | 0 | 2 |
| T7A.6 Ensuring effective procedures of linkage of HIV positive patients | 4 | 3 | 2 | 1 | 0 | 3 |
| T7A.7 Ensuring documentation of linkage of HIV positive patients | 4 | 3 | 2 | 1 | 0 | 2 |
| T7A.8 Training and providing refresher training to HIV testing counsellors | 4 | 3 | 2 | 1 | 0 | 3 |
| T7A.9 HTS quality monitoring including conducting observed practices for HTS counsellors and ensuring participation in proficiency testing | 4 | 3 | 2 | 1 | 0 | 3 |
| T7A.10 Providing transport and airtime for follow up and testing of sexual and other contacts including family members of HIV positive clients | 4 | 3 | 2 | 1 | 0 | 4 |
| T7A.11 Documenting, tracking and reporting ART, PEP and PrEP among those eligible | 4 | 3 | 2 | 1 | 0 | 2 |
| Total Implementing Partner = |  |  |  |  |  | 29 |  |  |  |  | 29 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Involvement of IP identification and linkage: ☒ 44–29: High ☐ 28–14: Medium ☐ 13–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |

## Indicator T7B: Transition of Patient identification and linkage to treatment : Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB PATIENT IDENTIFICATION AND LINKAGE TO TREATMENT ? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T7B.1 Recruitment of HIV testing services (HTS) counselors | 0 | 1 | 2 | 3 | 4 | 2 |
| T7B.2 Remuneration of HIV testing counselors (Funds for paying HTS Counselors) | 0 | 1 | 2 | 3 | 4 | 1 |
| T7B.3 Ensuring that HTS eligibility screening registers and SOPS are available | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.4 Ensuring that HIV testing consumables/supplies e.g. methylated spirit, gloves lancets etc. are available | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.5 Ensuring availability of adequate and appropriate HIV testing space/ environment | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.6 Ensuring effective procedures of linkage of HIV positive patients | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.7 Ensuring documentation of linkage of HIV positive patients | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.8 Training and providing refresher training to HIV testing counsellors | 0 | 1 | 2 | 3 | 4 | 2 |
| T7B.9 HTS quality monitoring including conducting observed practices for HTS counsellors and ensuring participation in proficiency testing | 0 | 1 | 2 | 3 | 4 | 3 |
| T7B.10 Providing transport and airtime for follow up and testing of sexual and other contacts including family members of HIV positive clients | 0 | 1 | 2 | 3 | 4 | 0 |
| T7B.11 Documenting, tracking and reporting ART, PEP and PrEP among those eligible | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 25 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in identification and linkage: ☐ 0–13: Low ☒ 14–28: Medium ☐ 29–43: High ☐ 44: Full Autonomy |  |  |  |  |  |  |

Comments

# CoUNTY LEVEL PATIENT RETENTION, ADHERENCE AND VIRAL SUPPRESSION SERVICES

## Indicator T8A: Transition of Patient retention, adherence and Viral suppression services: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of TRANSITION OF HIV/TB RETENTION, ADHERENCE AND VIRAL SUPPRESSION SERVICES ? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T8A.1 Provision of patient referral forms, appointment diaries and defaulter management tools to facilities. | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.2 Ensuring effective procedure to track missed appointments of patients on treatment | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.3 Ensuring effective procedures and tracking of referrals and transfers between health facilities | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.4. Ensuring effective procedures and tracking of referrals between different units within the same health facility | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.5 Paying allowances to track and bring patients with missed appointments or lost to follow-up back to care and tracking retention at site level | 4 | 3 | 2 | 1 | 0 | 4 |
| T8A.6. Paying allowances to community health volunteers for HIV/TB related activities | 4 | 3 | 2 | 1 | 0 | 4 |
| T8A.7. Supporting of patient support groups for HIV/TB related activities | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.8 Linking facilities with community groups supporting PLHIV/TB for patient follow-up and support | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.9 Strengthening on patient cohort analysis and reporting e.g. through training HF staff on preparing various reports | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.10 Ensure dissemination/updates of the most updated treatment guidelines | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.11 Supporting enhanced adherence counselling for patients with poor adherence | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.12 Supporting HIV/TB treatment optimization ensuring all cases are on an appropriate regimen | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.13 Funding /Supporting MDT meetings to discuss difficult HIV/TB cases | 4 | 3 | 2 | 1 | 0 | 3 |
| T8A.14 Tracking Viral suppression rates by population at site level – identify gaps and monitor progress | 4 | 3 | 2 | 1 | 0 | 3 |
| Total Implementing Partner = |  |  |  |  |  | 44 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Involvement of IP in retention and viral suppression: ☒ 56–38: High ☐ 37–19: Medium ☐ 18–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |

## Indicator T8B: Transition of Patient retention, adherence and Viral suppression services: : Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of TRANSITION OF HIV/TB RETENTION, ADHERENCE AND VIRAL SUPPRESSION SERVICES? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T8B.1 Provision of patient referral forms appointment diaries and defaulter management tools to facilities. | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.2 Ensuring effective procedure to track missed appointments of patients on treatment | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.3 Ensuring effective procedures and tracking of referrals and transfers between health facilities | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.4. Ensuring effective procedures and tracking of referrals between different units within the same health facility | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.5 Paying for processes to track and bring patients with missed appointments or lost to follow-up back to care tracking retention at site level | 0 | 1 | 2 | 3 | 4 | 0 |
| T8B.6. Funding community health volunteers and patient support groups | 0 | 1 | 2 | 3 | 4 | 0 |
| T8B.7 Linking facilities with community groups supporting PLHIV for patient follow-up and support | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.8 Provide funding for community visits to track patients | 0 | 1 | 2 | 3 | 4 | 0 |
| T8B.9 Strengthening on patient cohort analysis and reporting e.g. through training HF staff on preparing various reports | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.10 Ensure dissemination/updates of the most updated treatment guidelines | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.11 Supporting enhanced adherence counselling for patients with poor adherence | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.12 Supporting HIV treatment optimization ensuring all cases are on an appropriate regimen | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.13 Funding /Supporting MDT meetings to discuss difficult HIV cases | 0 | 1 | 2 | 3 | 4 | 3 |
| T8B.14 Tracking Viral suppression rates by population at site level – identify gaps and monitor progress | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 33 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in retention and viral suppression: ☐ 0–18: Low ☐ 19–36: Medium ☐ 37–55: High ☐ 56: Full Autonomy |  |  |  |  |  |  |

Comments

# COUNTY LEVEL HIV PREVENTION AND KEY POPULATION SERVICES

## Indicator T9A: Transition of HIV/TB prevention and Key population services : Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB PREVENTION AND KEY POPULATION SERVICES ? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T9A.1 Conducting targeted HIV testing of Members of Key population groups | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.2 Providing AGYW services for HIV prevention in safe spaces or Youth friendly settings and in Health facilities | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.3 Providing VMMC services for HIV prevention | 4 | 3 | 2 | 1 | 0 | 0 |
| T9A.4 Providing condoms and lubricants to members of Key populations | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.5 Provision of KP friendly services including provision of safe spaces | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.6 Providing PrEP to all HIV negative clients at risk of HIV but specifically targeting AGYW, KPs, Discordant couples, Pregnant and Breastfeeding women and Men at High risk . | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.7 Provision of Post Exposure Prophylaxis | 4 | 3 | 2 | 1 | 0 | 1 |
| T9A.8 Conducting outreach to Key population hot spots to increase enrollment | 4 | 3 | 2 | 1 | 0 | 3 |
| T9A.9 Tracking of enrollment into HIV prevention services and outcomes in Key populations | 4 | 3 | 2 | 1 | 0 | 3 |
| Total Implementing Partner = |  |  |  |  |  | 22 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of IP Involvement of HIV prevention and key population services : ☐ 36–24: High ☒ 23–12: Medium ☐ 11–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |

## Indicator T9B: Transition of HIV prevention and Key population services : Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB PREVENTION AND KEY POPULATION SERVICES ? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Not involved |  | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| T9B.1 Conducting targeted HIV testing of Members of priority population groups including key populations, discordant, and adolescent/young women etc | 0 |  | 1 | 2 | 3 | 4 | 3 |
| T9B.2 Providing AGYW services for HIV prevention in safe spaces or Youth friendly settings and in Health facilities | 0 |  | 1 | 2 | 3 | 4 | 2 |
| T9B.3 Providing VMMC services for HIV prevention | 0 |  | 1 | 2 | 3 | 4 | 0 |
| T9B.4 Providing condoms and lubricants to members of Key populations | 0 |  | 1 | 2 | 3 | 4 | 3 |
| T9B.5 Provision of KP friendly services to including provision of safe spaces | 0 |  | 1 | 2 | 3 | 4 | 3 |
| T9B.6 Providing PrEP to all HIV negative clients at risk of HIV but specifically targeting AGYW, KPs, Discordant couples, Pregnant and Breastfeeding women and Men at High risk in discordant relationship | 0 |  | 1 | 2 | 3 | 4 | 3 |
| T9B.7 Provision of Post Exposure Prophylaxis | 0 |  | 1 | 2 | 3 | 4 | 4 |
| T9B.8 Conducting outreach to Key population hot spots to increase enrollment | 0 |  | 1 | 2 | 3 | 4 | 3 |
| T9B.9 Tracking of enrollment into HIV prevention services and outcomes by populations | 0 |  | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  |  | 24 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of CDOH Involvement of HIV prevention and key population services : ☐ 0–11: Low ☐ 12–23: Medium ☒ 24–35: High ☐ 36: Full Autonomy |  |  |  |  |  |  |  |

Comments

*For TB6 if PrEP provision covers only some of the vulnerable groups mentioned, award 1 point

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL FINANCE MANAGEMENT

## Indicator T10A: Transition of Financial Management: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of FINANCIAL MANAGEMENT? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T10A.1 Preparing an annual county budget which integrates HIV care & treatment | 4 |  | 3 | 2 | 1 | 0 | 1 |  |
| T10A.2 Allocating available program resources | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T10A.3 Tracking program expenditures and income | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T10A.4 Producing financial reports | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T10A.5 Reallocating funding to respond to budget variances and program needs | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T10A.6 Conducts external audit | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T10A.7 Responding to audits/reviews | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T10A.8 Funding the overall county HIV/TB response (HIV/TB funding for the past 5 years) | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T10A.9 Reducing the HIV/TB response funding as a result of the county’s domestic resource mobilization (HIV/TB funding for the last FY) | 4 |  | 3 | 2 | 1 | 0 | 0 |  |
| Total Implementing Partner = |  |  |  |  |  |  | 27 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |
| Level of Involvement of the IP in Financial Management: ☒ 36–24: High ☐ 23–12: Medium ☐ 11–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |

## Indicator T10B: Transition of Financial Management: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB FINANCIAL MANAGEMENT? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T10B.1 Preparing an annual county budget which integrates HIV/TB care & treatment | 0 | 1 | 2 | 3 | 4 | 2 |
| T10B.2 Allocating available program resources | 0 | 1 | 2 | 3 | 4 | 2 |
| T10B.3 Tracking program expenditures and income | 0 | 1 | 2 | 3 | 4 | 1 |
| T10B.4 Producing financial reports | 0 | 1 | 2 | 3 | 4 | 4 |
| T10B.5 Reallocating funding to respond to budget variances and program needs | 0 | 1 | 2 | 3 | 4 | 2 |
| T10B.6 Conducts external audit | 0 | 1 | 2 | 3 | 4 | 2 |
| T10B.7 Responding to audits/reviews | 0 | 1 | 2 | 3 | 4 | 2 |
| T10A.8 Funding the overall county HIV/TB response (HIV/TB funding for the past 5 years) | 0 | 1 | 2 | 3 | 4 | 1 |
| T10A.9 Increasing the county’s HIV/TB response funding as part of its domestic resource mobilization (HIV/TB funding for the last FY) | 0 | 1 | 2 | 3 | 4 | 1 |
| Total CDOH = |  |  |  |  |  | 17 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Financial Management: ☐ 0–11: Low ☒ 12–23: Medium ☐ 24–35: High ☐ 36: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL MANAGING SUB-GRANTS OR OTHER GRANTS/COOPERATIVE AGREEMENTS

## Indicator T11A: Transition of Managing Sub-Grants other Grants/Cooperative Agreements: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB MANAGING SUB-GRANTS OR OTHER GRANTS/COOPERATIVE AGREEMENTS? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T11A.1 Defining the TOR for last/renewed sub-grant | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T11A.2 Planning and developing the budget | 4 |  | 3 | 2 | 1 | 0 | 0 |  |
| T11A.3 Managing the competitive bidding process for procurements/purchases | 4 |  | 3 | 2 | 1 | 0 | 0 |  |
| T11A.4 Tracking sub-grant expenditures | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T11A.5 Disbursing funds for procurements/purchases | 4 |  | 3 | 2 | 1 | 0 | 0 |  |
| T11A.6 Reporting results | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| Total Implementing Partner = |  |  |  |  |  |  | 10 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |
| Level of Involvement of the IP in Managing Sub-Grants: ☐ 24–16: High ☒ 15–8: Medium ☐ 7–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |

## Indicator T11B: Transition of Managing Sub-Grants other Grants/Cooperative Agreements: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB MANAGING SUB-GRANTS OR OTHER GRANTS/COOPERATIVE AGREEMENTS? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T11B.1 Defining the TOR for last/renewed sub-grant | 0 | 1 | 2 | 3 | 4 | 1 |
| T11B.2 Planning and developing the budget | 0 | 1 | 2 | 3 | 4 | 4 |
| T11B.3 Managing the competitive bidding process for procurements/purchases | 0 | 1 | 2 | 3 | 4 | 4 |
| T11B.4 Tracking sub-grant expenditures | 0 | 1 | 2 | 3 | 4 | 4 |
| T11B.5 Disbursing funds for procurements/purchases | 0 | 1 | 2 | 3 | 4 | 4 |
| T11B.6 Reporting results | 0 | 1 | 2 | 3 | 4 | 4 |
| Total CDOH = |  |  |  |  |  | 21 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in Managing Sub-Grants: ☐ 0–7: Low ☐ 8–15: Medium ☒ 16–23: High ☐ 24: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL COMMODITIES MANAGEMENT

## Indicator T12A: Transition of Commodities Management: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB COMMODITIES MANAGEMENT? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T12A.1 Developing/adapting commodity supply chain SOPs | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T12A.2 Monitoring consumption of ARVs, anti-TB drugs, Cotrimoxazole, HIV test kits, phlebotomy supplies, cryovials for HIV VL, DBS bundles, GeneXpert catrigdes, sputum mugs (other specific laboratory commodities?) | 4 |  | 3 | 2 | 1 | 0 | 2 |
| T12A.3 Monthly commodities reporting | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T12A.4 Building capacity/training of HF pharmacy and laboratory staff in commodity management | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T12A.5 Managing commodity storage spaces within the facilities | 4 |  | 3 | 2 | 1 | 0 | 2 |
| T12A.6 Submitting stock orders to National level supply chain organization e.g. NASCOP, KEMSA, etc | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T12A.7 Distributing supplies to testing sites, treatment facilities and labs | 4 |  | 3 | 2 | 1 | 0 | 3 |
| Total Implementing Partner = |  |  |  |  |  |  | 19 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of Involvement of the IP in Commodities Management: ☒ 28–19: High ☐ 18–9: Medium ☐ 8–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |

## Indicator T12B: Transition of Commodities Management: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB Commodities MANAGEMENT? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T12B.1 Developing/adapting commodity supply chain SOPs | 0 | 1 | 2 | 3 | 4 | 2 |
| T12B.2 Monitoring consumption of ARVs, anti-TB drugs, Cotrimoxazole, HIV test kits, phlebotomy supplies, cryovials for HIV VL, DBS bundles, Gene Xpert catrigdes, sputum mugs (other specific laboratory commodities?) | 0 | 1 | 2 | 3 | 4 | 3 |
| T12B.3 Monthly commodities reporting | 0 | 1 | 2 | 3 | 4 | 2 |
| T12B.4 Building capacity/training of HF pharmacy and laboratory staff in commodity management | 0 | 1 | 2 | 3 | 4 | 2 |
| T12B.5 Managing commodity storage spaces within the facilities | 0 | 1 | 2 | 3 | 4 | 3 |
| T12B.6 Submitting stock orders to National level supply chain organization e.g. NASCOP, KEMSA, etc | 0 | 1 | 2 | 3 | 4 | 3 |
| T12B.7 Distributing supplies to testing sites, treatment facilities and labs | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 18 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Pharmacy Management: ☐ 0–8: Low ☐ 9–17: Medium ☒ 18-27: High ☐ 28: Full Autonomy |  |  |  |  |  |  |

Comments

- T12A.2: There are SOPs that the IP is not involed in developing - T12A.5: The IPs generally not supported to do major renovations - T12B.1: Some SOPs are trickled down from the national - T12B.3: the county depend on partner support for transmitting the reports - T12B.4: Minimal trainings supported entirely by he county

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL EQUIPMENT PROCUREMENT AND USE

## Indicator T13A: Transition of Equipment Procurement and Use: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB EQUIPMENT PROCUREMENT AND USE? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T13A.1 Determining the need for key HIV/TB specific equipment (Fridges, freezers, centrifuges, Biosafety cabinets, CD4 machines, Gene Xpert machines, etc.) | 4 |  | 3 | 2 | 1 | 0 | 1 |
| T13A.2 Establishing equipment quantification and need based Prioritization of equipment | 4 |  | 3 | 2 | 1 | 0 | 1 |
| T13A.3 Development of specifications, ordering/procuring equipments | 4 |  | 3 | 2 | 1 | 0 | 1 |
| T13A.4 Funding equipment procurement | 4 |  | 3 | 2 | 1 | 0 | 1 |
| T13A.5 Maintaining and calibrating/certifying equipments | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T13A.6 Equipment inventory, supervising and training use of equipments | 4 |  | 3 | 2 | 1 | 0 | 2 |
| Total Implementing Partner = |  |  |  |  |  |  | 9 |  |  |  |  | 3 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of Involvement of the IP in Equipment Procurement and Management: ☐ 24–16: High ☒ 15–8: Medium ☐ 7–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |

## Indicator T13B: Transition of Procurement and Use: Level of Autonomy of the CountyCDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB EQUIPMENT PROCUREMENT AND USE? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T13B.1 Determining the need for key HIV/TB specific equipment (Fridges, freezers, centrifuges, Biosafety cabinets, CD4 machines, Gene Xpert machines, etc.) | 0 | 1 | 2 | 3 | 4 | 3 |
| T13B.2 Establishing equipment quantification and need based Prioritization of equipment | 0 | 1 | 2 | 3 | 4 | 3 |
| T13B.3 Development of specifications, ordering/procuring equipments | 0 | 1 | 2 | 3 | 4 | 3 |
| T13B.4 Funding equipment procurement | 0 | 1 | 2 | 3 | 4 | 2 |
| T13B.5 Maintaining and calibrating/certifying equipments | 0 | 1 | 2 | 3 | 4 | 2 |
| T13B.6 Equipment inventory, supervising and training use of equipments | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 16 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Supervision: ☐ 0–7: Low ☐ 8–15: Medium ☒ 16–23: High ☐ 24: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL LABORATORY SERVICES

## Indicator T14A: Transition of Laboratory Services: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB LABORATORY SERVICES? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T14A.1 Distributing QC proficiency testing panels and proficiency testing kits (GeneXpert and RHT) | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.2 Re-Distributing EQA proficiency testing panels and proficiency testing kits (GeneXpert and RHT) | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.3 Compiling and reporting on proficiency testing results | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.4 Conducting supervision/CAPA visits to laboratories | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.5 Training laboratory and HTS staff on good practices | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.6 Ordering laboratory reagents | 4 | 3 | 2 | 1 | 0 | 1 |
| T14A.7 Ordering laboratory consumables | 4 | 3 | 2 | 1 | 0 | 2 |
| T14A.8 Funding and Managing specimen transport systems (CD4, EID, VL, Gene Xpert, DST) | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.9 Monitoring TAT for test results (CD4, EID, VL, Gene Xpert, DST) | 4 | 3 | 2 | 1 | 0 | 2 |
| T14A.10 Implementing laboratory quality management systems (QMS) for HIV/TB | 4 | 3 | 2 | 1 | 0 | 3 |
| T14A.11 Supporting biosafety activities and health care waste management | 4 | 3 | 2 | 1 | 0 | 2 |
| T14A.12 Supporting service and maintenance contracts for laboratory equipment | 4 | 3 | 2 | 1 | 0 | 2 |
| Total Implementing Partner = |  |  |  |  |  | 30 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Involvement of the IP in Laboratory Services: ☐ 48–32: High ☐ 31–16: Medium ☐ 15–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |

## Indicator T14B: Transition of Laboratory Services: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB LABORATORY SERVICES? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T14B.1 Distributing QC proficiency testing panels and proficiency testing kits (GeneXpert and RHT) | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.2 Re-Distributing EQA proficiency testing panels and proficiency testing kits (GeneXpert and RHT) | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.3 Compiling and reporting on proficiency testing results | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.4 Conducting supervision/CAPA visits to laboratories | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.5 Training laboratory and HTS staff on good practices | 0 | 1 | 2 | 3 | 4 | 1 |
| T14B.6 Ordering laboratory reagents | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.7 Ordering laboratory consumables | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.8 Funding and Managing specimen transport systems (CD4, EID, VL, Gene Xpert, DST) | 0 | 1 | 2 | 3 | 4 | 1 |
| T14B.9 Monitoring TAT for test results (CD4, EID, VL, Gene Xpert, DST) | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.10 Implementing laboratory quality management systems (QMS) for HIV/TB | 0 | 1 | 2 | 3 | 4 | 3 |
| T14B.11 Supporting biosafety activities and health care waste management | 0 | 1 | 2 | 3 | 4 | 2 |
| T45B.12 Supporting service and maintenance contracts for laboratory equipment | 0 | 1 | 2 | 3 | 4 | 2 |
| Total CDOH = |  |  |  |  |  | 30 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Laboratory Services: ☐ 0–15: Low ☐ 16–31: Medium ☐ 32–47: High ☐ 48: Full Autonomy |  |  |  |  |  |  |

Comments

The support for lab equipment and services, as currently obtaining, is equally supported by both the IP and CDOH

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL INVENTORY MANAGEMENT

## Indicator T15A: Transition of Inventory Management for Equipment & Commodities: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB INVENTORY MANAGEMENT? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T15A.1 Needs determination function which develops quantity and resource requirements, consisting of Inventory Planning and Budgeting | 4 | 3 | 2 | 1 | 0 | 1 |
| T15A.2 Inventory in storage function including Receipt and Inspection process, and Storing process – (verify Ordering and Commodities/ Stores list updated on transactional basis) | 4 | 3 | 2 | 1 | 0 | 1 |
| T15A.3 Inventory Disposition Function including Loaning, Issuing and, Disposal Processes – (Check USG Assets & Equipment Disposal Guidelines) | 4 | 3 | 2 | 1 | 0 | 0 |
| T15A.4 Program monitoring function of Inventory control which provides sufficient transaction audit trails to support balances of inventory on the IP’s General Ledger – (verify annual Assets Inventory Audit Report) | 4 | 3 | 2 | 1 | 0 | 2 |
| T15A.5 Designated qualified and certified Supply Chain Management professional and, membership | 4 | 3 | 2 | 1 | 0 | 3 |
| T15A.6 Oversight Supervision of the Inventory Management functions | 4 | 3 | 2 | 1 | 0 | 2 |
| Total Implementing Partner = |  |  |  |  |  | 9 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Involvement of the IP in Inventory Management: ☐ 24–16: High ☐ 15–8: Medium ☐ 7–1: High ☐ 0: Phased out |  |  |  |  |  |  |

## Indicator T15B: Transition of Inventory Management for Equipment & Commodities: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB INVENTORY MANAGEMENT? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T15B.1 Needs determination function which develops quantity and resource requirements, consisting of Inventory Planning and Budgeting | 0 | 1 | 2 | 3 | 4 | 3 |
| T15B.2 Inventory in storage function including Receipt and Inspection process, and Storing process – (verify Ordering and Commodities/ Stores list updated on transactional basis) | 0 | 1 | 2 | 3 | 4 | 3 |
| T15B.3 Inventory Disposition Function including Loaning, Issuing and, Disposal Processes – (Check MOH-GOK Public Procurement & Asset Disposal Regulations, 2020) | 0 | 1 | 2 | 3 | 4 | 3 |
| T15B.4 Program monitoring function of Inventory control which provides sufficient transaction audit trails to support balances of inventory on the IP’s General Ledger – (verify annual Assets Inventory Audit Report) | 0 | 1 | 2 | 3 | 4 | 3 |
| T15B.5 Designated qualified and certified Supply Chain Management professional | 0 | 1 | 2 | 3 | 4 | 2 |
| T15B.6 Oversight Supervision of the Inventory Management functions | 0 | 1 | 2 | 3 | 4 | 3 |
| Total CDOH = |  |  |  |  |  | 17 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Supervision: ☐ 0–7: Low ☐ 8–15: Medium ☐ 16–23: High ☐ 24: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL IN-SERVICE TRAINING

## Indicator T16A: Transition of In-service Training: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB IN-SERVICE TRAINING? | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T16A.1 Assessing staff training needs | 4 | 3 | 2 | 1 | 0 | 3 |
| T16A.2 Selecting/adapting curricula | 4 | 3 | 2 | 1 | 0 | 3 |
| T16A.3 Planning training schedule | 4 | 3 | 2 | 1 | 0 | 3 |
| T16A.4 Arranging/funding/providing training venue | 4 | 3 | 2 | 1 | 0 | 4 |
| T16A.5 Providing or paying trainers/facilitators | 4 | 3 | 2 | 1 | 0 | 4 |
| T16A.6 Paying participant per diem | 4 | 3 | 2 | 1 | 0 | 4 |
| T16A.7 Use of integrated human resource information system (iHRIS Train) | 4 | 3 | 2 | 1 | 0 | 1 |
| Total Implementing Partner = |  |  |  |  |  | 22 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Involvement of the IP in In-Service Training: ☒ 28–19: High ☐ 18–9: Medium ☐ 8–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |

## Indicator T16B: Transition of In-service Training: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB IN-SERVICE TRAINING? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T16B.1 Assessing staff training needs | 0 | 1 | 2 | 3 | 4 | 3 |
| T16B.2 Selecting/adapting curricula | 0 | 1 | 2 | 3 | 4 | 2 |
| T16B.3 Planning training schedule | 0 | 1 | 2 | 3 | 4 | 3 |
| T16B.4 Arranging/funding/providing training venue | 0 | 1 | 2 | 3 | 4 | 1 |
| T16B.5 Providing or paying trainers/facilitators | 0 | 1 | 2 | 3 | 4 | 0 |
| T16B.6 Paying participant per diem | 0 | 1 | 2 | 3 | 4 | 0 |
| T15B.7 Use of integrated human resource information system (iHRIS Train) | 0 | 1 | 2 | 3 | 4 | 0 |
| Total CDOH = |  |  |  |  |  | 9 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of the CDOH in Supervision: ☐ 0–8: Low ☒ 9–17: Medium ☐ 18–27: High ☐ 28: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL HUMAN RESOURCE MANAGEMENT

## Indicator T17A: Transition of HIV/TB Human Resource Management: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB HUMAN RESOURCE MANAGEMENT? |  |  |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation |  | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |  |
| T17A.1 Presence of active of county public service board that recruits HIV/TB services staff (check: Gazette notice, minutes of meeting proceedings) | 4 |  | 3 |  | 2 | 1 | 0 | 0 |  |  |
| T17A.2 Determining staffing needs for the HIV/TB program | 4 |  | 3 |  | 2 | 1 | 0 | 2 |  |  |
| T17A.3 Advertising/posting positions for the HIV/TB program | 4 |  | 3 |  | 2 | 1 | 0 | 1 |  |  |
| T17A.4 Shortlisting/interviewing candidates for the HIV/TB program | 4 |  | 3 |  | 2 | 1 | 0 | 2 |  |  |
| T17A.5 Performance appraisal for the HIV/TB program | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |  |
| T17A.6 Paying staff salaries for the HIV/TB program | 4 |  | 3 |  | 2 | 1 | 0 | 4 |  |  |
| T17A.7 Appointing HIV/TB program staff (recruitment) | 4 |  | 3 |  | 2 | 1 | 0 | 0 |  |  |
| T17A.8 Absorbing previously IP recruited staff through the county public service board (transitioned staff) | 4 |  | 3 |  | 2 | 1 | 0 | 2 |  |  |
| T17A.9 Supporting facilities to effectively utilize the few available staff to execute health facility roles e.g. development of task shifting plans at health facilities | 4 |  | 3 |  | 2 | 1 | 0 | 3 |  |  |
| T17A.10 Use of integrated human resource information system (iHRS) (government HRH management and development) | 4 |  | 3 |  | 2 | 1 | 0 | 4 |  |  |
| Total Implementing Partner = |  |  |  |  |  |  |  | 21 |  |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |  |  |
| Level of Involvement of IP in HR Management: ☐ 40–27: High ☒ 26–13: Medium ☐ 12–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |  |  |

## Indicator T17B: Transition of HIV/TB Human Resource Management: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB HUMAN RESOURCE MANAGEMENT? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T17B.1 Presence of active of county public service board that recruits HIV/TB services staff (check: Gazette notice, minutes of meeting proceedings) | 0 | 1 | 2 | 3 | 4 | 4 |
| T17B.2 Determining staffing needs for the HIV/TB program | 0 | 1 | 2 | 3 | 4 | 3 |
| T17B.3 Advertising/posting positions for the HIV/TB program | 0 | 1 | 2 | 3 | 4 | 4 |
| T17B.4 Shortlisting/interviewing candidates for the HIV/TB program | 0 | 1 | 2 | 3 | 4 | 3 |
| T17B.5 Performance appraisal for the HIV/TB program | 0 | 1 | 2 | 3 | 4 | 3 |
| T17B.6 Paying staff salaries for the HIV/TB program | 0 | 1 | 2 | 3 | 4 | 2 |
| T17B.7 Appointing HIV/TB program staff (recruitment) | 0 | 1 | 2 | 3 | 4 | 2 |
| T17B.8 Absorbing previously IP recruited staff through the county public service board (transitioned staff) | 0 | 1 | 2 | 3 | 4 | 2 |
| T17B.9 Supporting facilities to effectively utilize the few available staff to execute health facility roles e.g. development of task shifting plans at health facilities | 0 | 1 | 2 | 3 | 4 | 3 |
| T17B.10 Use of integrated human resource information system (iHRS) (government HRH management and development) | 0 | 1 | 2 | 3 | 4 | 2 |
| Total CDOH = |  |  |  |  |  | 28 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in HR Management: ☐ 0–12: Low ☐ 13–26: Medium ☒ 27–39: High ☐ 40: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL HIV/TB PROGRAM DATA MANAGEMENT

## Indicator T18A: Transition of HIV/TB Program Data Management: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of HIV/TB DATA MANAGEMENT? (Verify using reports, minutes, etc) |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |  |
| T18A.1 Collecting and entering data from facilities in to DHIS2 | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T18A.2 Collecting and entering data from facilities in to DATIM | 4 |  | 3 | 2 | 1 | 0 | 4 |  |
| T18A.3 Checking completeness and accuracy | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T18A.4 Conduct DQA on regular basis | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T18A.5 Giving feedback and support to facilities for data quality | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T18A.6 Analyzing data and producing reports sent to MOH | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T18A.7 Monitoring results and determining remedial actions | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| T18A.8 Managing IT infrastructure for HIV/TB data management | 4 |  | 3 | 2 | 1 | 0 | 3 |  |
| T18A.9 Training & mentorship of health facility staff in data management | 4 |  | 3 | 2 | 1 | 0 | 2 |  |
| Total Implementing Partner = |  |  |  |  |  |  | 22 |  |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |  |
| Level of Involvement of IP in Data Management: ☐ 36–24: High ☐ 23–12: Medium ☐ 11–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |  |

## Indicator T18B: Transition of HIV/TB Program Data Management: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of HIV/TB DATA MANAGEMENT? (Verify using reports, minutes, etc) | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T18B.1 Collecting and entering data from facilities in to DHIS2 | 0 | 1 | 2 | 3 | 4 | 3 |
| T18B.2 Collecting and entering data from facilities in to DATIM | 0 | 1 | 2 | 3 | 4 | 0 |
| T18B.3 Checking completeness and accuracy | 0 | 1 | 2 | 3 | 4 | 2 |
| T18B.4 Conduct DQA on regular basis | 0 | 1 | 2 | 3 | 4 | 1 |
| T18B.5 Giving feedback and support to facilities for data quality | 0 | 1 | 2 | 3 | 4 | 2 |
| T18B.6 Analyzing data and producing reports sent to MOH | 0 | 1 | 2 | 3 | 4 | 2 |
| T18B.7 Monitoring results and determining remedial actions | 0 | 1 | 2 | 3 | 4 | 2 |
| T18B.8 Managing IT infrastructure for HIV/TB data management | 0 | 1 | 2 | 3 | 4 | 1 |
| T18B.9 Training & mentorship of health facility staff in data management | 0 | 1 | 2 | 3 | 4 | 2 |
| Total CDOH = |  |  |  |  |  | 15 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in Data Management: ☐ 0–11: Low ☐ 12–23: Medium ☐ 24–35: High ☐ 36: Full Autonomy |  |  |  |  |  |  |

Comments

TRANSITION BENCHMARKING INDICATOR REPORTING FORM

# COUNTY LEVEL PATIENT MONITORING SYSTEM

## Indicator T19A: Transition of Patient Monitoring System: Level of Involvement of the Implementing Partner

| To what degree is the Implementing Partner involved in each of the following aspects of the HIV/TB PATIENT MONITORING SYSTEM? |  | Enter the appropriate level for each item in the “Number” column. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Dominates implementation |  | Supportive role/ partial implementation | Involved in supportive role | Partial supportive role | Not involved (or only under contract to COUNTY HEALTH DEPARTMENT) | Number |
| T19A.1 Providing patient monitoring system/tools | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T19A.2 Entering patient data into the system/tools | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T19A.3 Checking completeness and accuracy | 4 |  | 3 | 2 | 1 | 0 | 2 |
| T19A.4 Analyzing data and producing reports | 4 |  | 3 | 2 | 1 | 0 | 2 |
| T19A.5 Tracking overall county lost-to-follow up, transfer, death & retention rates | 4 |  | 3 | 2 | 1 | 0 | 2 |
| T19A.6 Managing Electronic Medical Record systems for patient monitoring | 4 |  | 3 | 2 | 1 | 0 | 3 |
| T19A.7 Training Health facility staff in monitoring, evaluation & reporting (at least 2 of the three) | 4 |  | 3 | 2 | 1 | 0 | 2 |
| Total Implementing Partner = |  |  |  |  |  |  | 17 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |  |
| Level of Involvement of IP in Patient Monitoring System: ☐ 28–19: High ☐ 18–9: Medium ☐ 8–1: Low ☐ 0: Phased Out |  |  |  |  |  |  |  |

## Indicator T19B: Transition of Patient Monitoring System: Level of Autonomy of the CDOH

| To what degree is the CDOH involved in each of the following aspects of the HIV/TB PATIENT MONITORING SYSTEM? | Not involved | Minimally involved NOT independently | Involved in activity but NOT independent | Implements mostly NOT independently | Implements independently (or has contract with provider) | Number |
| --- | --- | --- | --- | --- | --- | --- |
| T19B.1 Providing patient monitoring system/tools | 0 | 1 | 2 | 3 | 4 | 1 |
| T19B.2 Entering patient data into the system | 0 | 1 | 2 | 3 | 4 | 2 |
| T19B.3 Checking completeness and accuracy | 0 | 1 | 2 | 3 | 4 | 2 |
| T19B.4 Analyzing data and producing reports | 0 | 1 | 2 | 3 | 4 | 2 |
| T19B.5 Tracking overall county lost-to-follow up, transfer, death & retention rates | 0 | 1 | 2 | 3 | 4 | 2 |
| T19B.6 Managing Electronic Medical Record systems for patient monitoring | 0 | 1 | 2 | 3 | 4 | 1 |
| T19B.7 Training Health facility staff in monitoring, evaluation & reporting (at least 2 of the three) | 0 | 1 | 2 | 3 | 4 | 2 |
| Total CDOH = |  |  |  |  |  | 12 |
| Use this total to determine the appropriate level below. |  |  |  |  |  |  |
| Level of Autonomy of CDOH in Patient Monitoring System: ☐ 0–8: Low ☐ 9–18: Medium ☐ 19–27 High ☐ 28: Full Autonomy |  |  |  |  |  |  |

Comments

INSTITUTIONAL OWNERSHIP INDICATORS

# COUNTY LEVEL INSTITUTIONAL OWNERSHIP INDICATOR

INSTITUTIONAL OWNERSHIP INDICATOR REPORTING FORM - COUNTY LEVEL

### Indicator IO.1:Operationalization of national HIV/TB plan at institutional level

| Select the value that indicates the appropriate level for each item and report the values in the “Number” column |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Components | No/not applicable | Few of the program components | About half of program components | Most of the program components | Complete program components | Number |
| - Does the county routinely develop HIV/TB AWPs that are based on the CIDP? | 0 | 1 | 2 | 3 | 4 |  |
| - Has the county costed its HIV/TB AWP and integrated it with the last national budget request? | 0 | 1 | 2 | 3 | 4 |  |
| - Are different levels of HIV/TB treatment staff involved in the development of the HIV/TB AWP? | 0 | 1 | 2 | 3 | 4 |  |
| - Are stakeholders from HIV/TB programs and PLHIV/TB involved in the development of HIV/TB AWPs? | 0 | 1 | 2 | 3 | 4 |  |
| - Is the implementation of the county HIV/TB work plan monitored and tracked by the County health team? | 0 | 1 | 2 | 3 | 4 |  |
| Total |  |  |  |  |  |  |
| Use this total to determine the appropriate level below (mark with “X”). |  |  |  |  |  |  |
| Operationalization of national HIV/TB plan at institutional level: ☐ 0-5: Very Weak ☐ 6-12: Weak ☐ 13-19: Intermediate ☐ 20: Strong |  |  |  |  |  |  |

Comments

INSTITUTIONAL OWNERSHIP INDICATOR REPORTING FORM - COUNTY LEVEL

### Indicator IO.2: Institutional coordination of HIV/TB prevention, care and treatment activities

| Select the value that indicates the appropriate level for each item and report the values in the “Number” column |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Components | No/not applicable | Few of the program components | About half of program components | Most of the program components | Complete program components | Number |
| - Does the CDOH have a list of all active HIV/TB services CSOs and implementing partners in the county with contact information? | 0 | 1 | 2 | 3 | 4 |  |
| - Does the county provide a functional forum for experience exchange on at least a quarterly basis? | 0 | 1 | 2 | 3 | 4 |  |
| - Does the county disseminate information, standards and best practices to implementers and stakeholders in a timely manner? | 0 | 1 | 2 | 3 | 4 |  |
| - Does the county work to ensure a rational geographic distribution, program coverage and scale-up of HIV/TB services? | 0 | 1 | 2 | 3 | 4 |  |
| Total |  |  |  |  |  |  |
| Use this total to determine the appropriate level below (mark with “X”). |  |  |  |  |  |  |
| Institutional coordination of HIV care and treatment activities: ☐ 0-4: Very Weak ☐ 5-9: Weak ☐ 10-15: Intermediate ☐ 16: Strong |  |  |  |  |  |  |

Comments

INSTITUTIONAL OWNERSHIP INDICATOR REPORTING FORM - COUNTY LEVEL

### Indicator IO.3: Congruence of expectations between levels of the health system

| Select the value that indicates the appropriate level for each item and report the values in the “Number” column |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Components | No/not applicable | Few of the program components | About half of program components | Most of the program components | Complete program components | Number |
| - Is the county strategic plan aligned to the National HIV/TB framework developed by NACC? (Can they explain the framework developed by NACC? Do they have a copy of the framework?) | 0 | 1 | 2 | 3 | 4 |  |
| - Does the county team perceive the national framework for HIV/TB care and treatment programs is relevant to their county needs and that it will help ensure the continued provision of services in their context? | 0 | 1 | 2 | 3 | 4 |  |
| - Is the policy formulation and capacity building functions of NACC/NASCOP to the county helpful in resolving implementation challenges for HIV/TB care and treatment services? | 0 | 1 | 2 | 3 | 4 |  |
| - Is the county team aware of its HIV/TB program service targets? If yes, are they using this data to inform annual HIV/TB plans? | 0 | 1 | 2 | 3 | 4 |  |
| - Does the county team perceive that the HIV service targets/objectives expected of their county are realistic? | 0 | 1 | 2 | 3 | 4 |  |
| - Is the financial grant from the national level adequate to meet the HIV/TB service targets expected of the county team? | 0 | 1 | 2 | 3 | 4 |  |
| Total |  |  |  |  |  |  |
| Use this total to determine the appropriate level below (mark with “X”). |  |  |  |  |  |  |
| Congruence of expectations between levels of the health system: ☐ 0-7: Very Weak ☐ 8-15: Weak ☐ 16-23: Intermediate ☐ 24: Strong |  |  |  |  |  |  |

Comments

Technical guidance to county refers to supporting county in effective planning and budgeting, intergration of partner workplans and budgets, strengthening M&E and data management, etc

Examples of technical support include formation of a multi-unit/division quality improvement team, Identification of specific areas for quality improvement such as infection control, waste management, clinical data audit to ensure record keeping compliance, and compliance with quality standards.